## PM Issue Tracking
PROJECT MANAGEMENT ISSUE TRACKING
COMPANY | VALTECH |  | STATUSES | STATUS TALLY | STATUSES | STATUS TALLY
DEPARTMENT | MACH STREAM BATCH |  | NOT STARTED | 0 | LOW | 2
PROJECT NAME | SPICELAND-ONLINE HOMEMADE SPICES AND SNACKS DELIVERY SYSTEM |  | IN PROGRESS | 2 | MEDIUM | 5
|  |  | CLOSED | 14 | HIGH | 9
ISSUE NO | ISSUE DESCRIPTION | STATUS | PRIORITY | ASSIGNEE | OPEN | CLOSED
1 | REGISTRATION PAGE-address fields refactor | CLOSED | LOW | SINDHU | 2022-12-01 | 13/1/2022
2 | LOGIN and REGISTRATION PAGE-frountend in React | CLOSED | MEDIUM | SINDHU | 13/1/2022 | 13/1/2022
3 | Login Service connect with microservices | CLOSED | HIGH | SINDHU | 2022-12-01 | 16/1/2022
4 | LOGIN PAGE-Validation | CLOSED | LOW | SINDHU | 16/1/2022 | 16/1/2022
6 | Vendor DASHBOARD-refactor JSP to REACT | CLOSED | HIGH | AKSHAY KUMAR K | 2022-12-01 | 16/1/2022
7 | Vendor dashboard-Visibility of product images in manage and update product functionality | IN PROGRESS | HIGH | AKSHAY KUMAR K | 16/1/2022 | ----
8 | DELIVERY PERSON-Location Based Delivery | CLOSED | MEDIUM | SANJAY | 16/1/2022 | 18/1/2022
9 | Vendor service fetch data through RestTemplate from login-Service | CLOSED | HIGH | AKSHAY KUMAR K | 18/1/2022 | 19/1/2022
10 | Functionality of one Seller selling one product to avoid duplicate entry of that product. | CLOSED | MEDIUM | AKSHAY KUMAR K | 19/1/2022 | 19/1/2022
11 | Delivery dashboard-refactor JSP to REACT | CLOSED | HIGH | SANJAY | 13/1/2022 | 13/18/2022
12 | Customer dashboard-refactor JSP to REACT | CLOSED | HIGH | DHEERAJ | 19/1/2022 | 24/1/2022
13 | Vendor list for same product in customer dashboard | CLOSED | MEDIUM | DHEERAJ | 16/12/2022 | 17/12/2022
14 | Mail service integrate with all other service | IN PROGRESS | HIGH | MOYUKH | 2022-01-12 | ------
15 | Admin dashboard-refactor JSP to REACT | CLOSED | HIGH | VARSHITHA | 13/1/2022 | 18/1/2022
16 | Page to page navigation in React | CLOSED | MEDIUM | VARSHITHA | 17/12/2022 | 25/12/2022

## PM Issue Tracking - BLANK
PROJECT MANAGEMENT ISSUE TRACKING TEMPLATE
COMPANY |  |  | STATUSES | STATUS TALLY | STATUSES | STATUS TALLY
DEPARTMENT |  |  | NOT STARTED | 0 | LOW | 0
PROJECT NAME |  |  | IN PROGRESS | 0 | MEDIUM | 0
PROJECT MANAGER |  |  | CLOSED | 0 | HIGH | 0
ISSUE NO | ISSUE DESCRIPTION | STATUS | PRIORITY | ASSIGNEE | OPEN | CLOSE | COMMENTS
CLICK HERE TO CREATE IN SMARTSHEET

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.